## Complete (hidden)
CAB WORKPLAN - Work Complete
RFC | Date Complete | Issue | Priority | Details | Action | Status
|  | NDR2010 Benefits Realisation | 1 | Implementation of recommendations affecting AO | IMS | Data cleansing exercise begun but will now be incorporated into NDR2015 project
RFC 2011-115 |  | Data Issues/ Security | 1 | Proposed restrictions on the ability to export data from AO and on user’s rights to view possibly sensitive/commercial in confidence information collected for valuation casework |  | COMPLETE
Lookup Table Change |  | External Application | 1 | External Application for List revision cases as AV’s don't generate certificates- or as this is a reasonable combination it should produce a R12D Cert • Remove ‘Already Valued’ as a selection when creating “request for list revision LPS or BC cases. LA/LO conclusion codes should be invalid. | ISG | AV now only for selection with External Application for List Revisions (A3s) COMPLETE
RFC 2011-119 |  | Web Applications | 1 | • Remove “other” as an option for generating a query on a property valuation. List as a telephone number to contact instead | ISG | Domestic and Non Domestic now complete
RFC 2012-006 |  | Web Applications | 1 | On case registration – attachment description details are not being populated which is a process that could be automated | ISG | COMPLETE
RFC 2012-007 |  | Web Applications | 1 | Amend tel no on web forms so as not restricted to 11 digits | ISG | COMPLETE
RFC 2012-005 |  | NIHE Exercise | 1 | Yearly undertaking – resourcing required | ISG | COMPLETE
RFC 2011-136 |  | Address alignment | 1 | • As the web lists are being used for address alignment, we should ensure that the web accurately reflects AO. Suggest undertaking a web - AO recon exercise | ISG | COMPLETE
RFC 2012-017 | 2012-02-16 | ABBACUS Revision Request Emails | 1 | • Add Prop_id, Ward and Address to ABBACUS Revision Request Emails (to allow for cases to be allocated without the valuer looking them up in AO) | ISG | COMPLETE
RFC 2012-016 | 2012-02-16 | Pointer File Validation Exercise | 1 | Undertake a Pointer Repository to Pointer csv file (06-Feb) validation exercise (ISG job as new address updates often appear in monthly csv files not in normal daily files) | ISG | COMPLETE
RFC 2012-006 | 2012-02-16 | Attachment Tab Default Description | 1 | Add Default Description to the attachment tab in case viewer for incoming web applications - it is mandatory on AO yet blank so staff inserting 'a's and '.'s | ISG | COMPLETE
RFC 2012-024 | 2012-02-23 | Amend telephone no on Ack Letters | 1 | Amending Tel No on the HQ Acknowledgement letter to 0300 200 7801 | ISG | Completed on 30 March 2012
RFC 2012-018 | 2012-02-24 | Pointer Interface | 1 | Add a new Category of 'L' to the daily outgoing XML file to Pointer from AO | ISG | COMPLETE
RFC 2012-026 | 2012-02-24 | Pointer Interface | 1 | Amend address checking to stop checking for duplicates on Misc case work | ISG | COMPLETE
RFC 2012-028 | 2012-02-24 | Case Allocation | 1 | Withdraw case allocataion rights for 4 staff in Bangor Office | ISG | COMPLETE
RFC 2012-029 | 2012-02-24 | Attachments | 1 | Provide R&B CR Team with access to Attachments | ISG | COMPLETE
RFC 2012-030 | 2012-02-24 | AO Names | 1 | Addition of new NID for Belfast City Council | ISG | COMPLETE
RFC 2012-031 | 2012-02-24 | Attachments | 1 | Provide more R&B Staff with access to Attachments | ISG | COMPLETE
RFC 2012-032 | 2012-02-24 | AO Cases | 2 | Update Transaction Inspection Flag on AO Cases | ISG | COMPLETE
RFC 2012-008 | 2012-02-15 | ABBACUS Interface | 2 | Add ABBACUS Revision Request ID to Case viewer | ISG | COMPLETE
RFC 2012-013 | 2012-02-15 | ABBACUS Interface | 2 | Amend Report information for the ABBACUS to AO RR Interface email | ISG | COMPLETE
RFC 2012-017 | 2012-02-15 | ABBACUS Interface | 2 | Add Prop_id, Ward and Address to ABBACUS Revision Request Emails - previously done for web apps | ISG | COMPLETE - March 2012
RFC 2012-038 | 2012-03-30 | The Arc - applications for review | 1 | Create 474 external requests for application review and link to the 474 properties in The Arc apartment complex on Queens Road inc interested parties details etc.. | ISG | Completed on 30 March 2012
RFC 2012-033 | 2012-02-24 | Web | 2 | Prevent Update to Web for Appeals Closing with a subsequent case in between them and originals | ISG | Completed on 30 March 2012
2011-118, 2012-019 | bf from previous workplan | Casework Tracking | 1 | Ability for ratepayers to track progress of application or appeal cases on-line (case reference number) | ISG | Completed on 30 March 2012
RFC 2011-132 | bf from previous workplan | Web Updates for Cloned Cases | 2 | • Billy arranged for a new relevant date to be added to the list entry tab to ensure that it always showed the correct latest valuation. One thing overlooked here was updating the web. • EXAMPLE: PID 998212 the correct value should be £4,350 but we have £3,450 on the web, because that is the value of the latest cases to close on the property • Problem is it a clone of a previous list entry and as there has been a subsequent case, then the value of the cloned case should not have gone to the web | IMS | Completed on 30 March 2012
RFC 2011-138 | bf from previous workplan | New transaction Inspection Case Type and Sub Type | 1 | • Needed for valuers acting in the role of Local Market Information Managers | ISG | Completed on 30 March 2012
RFC 2012-020 | 2012-02-15 | Completion Notice Dates | 2 | When reprinting Completion Notices, the date should show the date the completion notice was issued and not the date it is being reprinted (which is what is happening currently) | ISG | Completed on 30 March 2012
RFC 2012-037 | 2012-03-20 | Transfer Ack Letters to Reporting Service Format | 1 | Convert ACK letters to the more flexible RS format in line with certificates for release with casework tracking at end of March | ISG | Completed on 30 March 2012
RFC 2012-036 | 2012-03-20 | Completion Notice Appeals | 1 | Create a link between cloned CN cases and original ND or NN case to allow Relevant Dates in cloned cases to be written back to original NN / ND case | ISG | Completed on 30 March 2012
|  | automated ID removal |  |  |  | removed following discussion at previous CAB - not an AO issue.
RFC 2012-035 | 2012-03-13 | Abbacus Revision Requests | TBC | Remove 106 ABBACUS Revision Requests from the AB to AO interface as they are against Land Entries | ISG | now complete (20.04.12)
RFC 2012-023 | 2012-02-22 | Audit Log | 1 | Amend Audit Watch Routine to Exclude Nightly Interface Updates added to JMS as a Priority 1 job for target completion by 31 March. | ISG | COMPLETED 14th May
RFC 2012-044 | 2012-05-01 | ABBACUS Interface - Revisions against demolished properties | TBC | Functionality to be amended so that 'demolished' requests are dealt with automatically but still retained within AO, negating the need for weekly action to deal with them | ISG | Completed on 16th May
RFC 2012-050 | 2012-05-14 | Amend Occupier Info in CR File | 1 | Information currently not transferring from AO to Abbacus. Should include the first name in all CRs from now on | ISG | Completed on 17th May
RFC 2012-052 | 2012-05-16 | Formatted Web Address Change | 3 | When an AO address in not aligned with Pointer the web shows "Formatted Address not available for Property" but it is ok when the address is aligned. Remove the not available line | ISG | Completed on 23rd May
RFC 2012-054 | 2012-05-17 | Amend Population of CR file for Ratepayer Details | TBC | Amend population of CR file so that first name populates RP_Firstnamne and Surname / Company populates RP_Surname - currently both appear in the RP_Surname field as they did for after_occupier | ISG | Completed on 24th May
| bf from previous workplan | New age category for domestic property | 3 | • At present most recent age category is post-1990 • Suggestion that an additional category for, say, post-2010 is introduced | IMS | No further action - DC to speak to GG Completed 25th May
| bf from previous workplan | Land Entry Certificates | 2 | Change functionality for land entries so if interested parties is blank in property viewer – no certificate will generate. Any required certificates can be highlighted in the case viewer | IMS | Completed 25th May 2012
RFC 2012-021 | 2012-02-24 | Pointer Interface | 2 | Amend Web Submissions so that Demolition requests are logged as Challenges | ISG / IMS | COMPLETED 28th MAY 12
2012-02-16 |  | Web Submissions – Interested Party | 2 | Populate Interested Party information from web submissions - to prevent the need for staff to type this in from the web application | ISG | Completed and Live - 06/06/12
2012-02-16 | 27th June 2012 | Ready Reckoner | 2 | Windows 7 / Excel 2007 issue - Ready Reckoner not launching - although the system is W7 compliant we believe the RR not to be Excel 2007 ready | ISG | June 2012: To be released 2nd July.
2012-05-16 | 2012-06-30 | Prevent Sub-Type Changes to AV on ABBACUS RR Cases | 1 | Prevent Sub-Type Changes to AV on ABBACUS RR Cases as no CR is being returned to ABBACUS for those Revision Requests - happended to 70 so far | ISG | June 2012: Completed and rolled out to Live AO 02/07/12
bf from previous workplan | 2012-07-31 | Mass Removal of Properties from Valuation List | 3 | • VALUATION: Create 1 DV/HD case & Complete all required data input for case. • LCMG: Link case to identified properties. Delete 'Interested Parties' from properties. Delete all 'Property Part's/Domestic Details Notes Tab: CCNxxx Comment: Zero NAV - Hereditament Removal • VALUATION: Mass update Key Pane data as required • LCMG - Close case. CR file transfer to Abbacus (ICS) - separate file req The above will require the one-to-one case-to-property rule to be relaxed for this exercise | ISG | July 2012 - Complete
2012-06-14 |  | Web Apps Occupier Info | 1 | Population of Occupier information from Web Apps | ISG | Completed 31st July - Applied to Live
bf from previous workplan | see Update | Photo Attachments in Property Tab | 3 | Suggestions have been made concerning the linking of photo attachments twice i.e. in property and case viewer. Possible solutions suggested regard either an attachment viewer or link attachments made in case viewer to the property viewer e.g. a case attachment tab. | ISG | Complete
2012-04-16 | 2012-08-03 | NI Direct Information Assurance Principles for Casework Tracking | 1 | Enable the linking of the existing Casework Tracking functionality to the NIDirect website. Questionnaire complete and in TRIM | ISG | Now complete (03.08.12)
RFC 2012-067 | 2012-07-25 | Revision of Valuation Certificate Letter Wording |  | Alan Hazlett has requested change to wording or certificate cover letters. These have been reviewed and a document of changes created which includes new sentences to be included regarding appeals. | IMS/ISG | August 2012: New wording added to certificate wrapper and deployed to LIVE 03/08/12
243 | 2012-07-02 | 1 | 1 | To give customers more information regarding valuations |  | Live 02/07/2012
RFC 2012- 059 | 2012-09-10 | ABBACUS Revision Req - Case In Progress | 0.084722 | Actioning ABBACUS Revision Requests which are currently not registered as there is a case already in progress | IMS / ISG | Live
No RFC - Just changes to look up tables | 2012-09-10 | Time Recording activies | 1:1 | Ian Wort has reviewed the time recording options available on AO and has requested a number of changes | ISG | Live
RFC 2012-039 | 2012-10-02 | Attachment Tab Security | 1:1 | • Case Viewer : A User should only be able to link/unlink/amend attachments he/she has created when the case status is 'in Progress' And users should not be able to amend an attachment after a case is closed • Property Viewer: Attachment only editable when in progress case linked - once that case is closed attachment should not be editable when another in progress case linked | IMS / ISG | Live 02/10/12
RFC 2012 - 057 | 2012-09-30 | AO Contingency / Disaster Recovery Test | 1:1 | Compliance with NICS data Security requirements | ISG | Complete
NDR 2012-001 | 2012-09-30 | IT Audit | 1:1 | NDR Project plan requirement | ISG | Complete
NDR 2012-003 | 2012-09-30 | DA / CALc Knowledge Transfer | 1:1 | DA / CALc Knowledge Transfer for NDR 2015 | ISG | Complete
N/A | 2012-10-04 | Training Database Update | 1:01 | Training database to be updated to reflect current AO with a view to updating environment on a regular basis. | ISG | Complete
N/A | 2012-11-15 | Valuation Certificate Amendment | 1:1 | On the valuation certificate, the Date of Issue should match the date the case is closed | ISG | complete
1. RFC 2012-027 2.RFC 2012 - 041 3.RFC 2012-040 4.RFC-2012-042 | 2012-12-07 | Completion Notice | 1:1 | 1. For appealed CN’s currently cannot see info in ‘Completion Notice Information’ tab. This info should be cloned with the case but with the applicant details editable and CN dates defaulted to blank 2. Completion Notice Appeals New Cloning and Closing Requirements 3. Amend category, type and sub-types in look ups, updating open and closed CN cases, excluding these appeals from casework tracking, CRs and web updates 4.the non-domestic general letter to be ready for testing on Mary's return - awaiting templates for remainder of appeals / LT / NIVT, which will differ according to conc code | IMS ISG | complete
NDR 2012-008 | 2012-12-17 | AO- Web Recon for ND Properties | 1:1 | Ensure web property valuation reconcile 100% with the last list entry in AO. This task will be carried out pre-Christmas and scheduled to be re-executable at regular intervals ahead of key NDR project milestones to ensure that once 100% alignment is achieved, that it is maintained. | ISG | Complete
RFC 2012-051 | 2012-12-17 | Pointer - AO Address Validation changes |  | Decipher the current import address validation rules and provide them to Mary in a user friendly format then Apply any amendments proposed by Mary afterwards | ISG | complete
RFC 2012-058 RFC 2012-062 | 2012-12-17 | Amend the Pointer Interface, so that AO Address viewer is populated for IG Sheet and Plan No New Instructions for A2 Pointer generated rating cases | 1 | Add both Pointer Fields to AO Address and Property Viewers and if possible back populate the fields for all addresses that have been aligned with Pointer and that are on the current valuation list and back populate New Instructions for A2 Pointer generated rating cases | isg | Complete
RFC 2013-002 | 2013-01-22 | SSA Casework PCDs |  | amending default PCDs on SSA casework currently 15 days to 12 | ISG | Complete
RFC 2012-065 | 2012-11-30 | Rationalise AO user accounts |  | to keep handle on these as we pay SQL Licenses per seat and also from a performance pov - currently a hug increase in requests for new accounts from R&B, following re-organisation | ISG | Complete
NDR 2013-001 | 2013-01-02 |  | DA CALc installs for the NDR Reval Team |  | isg | complete
RFC 2012-070 | 2013-02-01 | Sun Interface charging following Grade changes |  | Currently Sun interface is programmed to charge at grade person was when closing case i.e. their current grade. Michelle Henry undertook chargeable work as a V1 and became an SV in May. Case only closing now, and all time charged at SV rate - involves 50 hours work and a difference of circa £2.5K, so this needs to be addressed, so that the interface can bill across grades in lifetime of same case. | isg | Complete
RFC 2012-069 | 2013-01-03 | Relevant Date Type Validation | 1 | Add additional validation to the case viewer, so when one of the "Relevant Date Type" is selected, then a relevant date must be entered | ISG IMS | Complete
RFC 2012-076 | N/a | Pointer Ward Validation | n/a | Include Ward in Pointer Interface Address Validation Checks : January 2013: removed from work plan pending further investigation. Currently not a viable option. | IMS ISG | Suspended
RFC 2012-012 |  | Pointer Emails | 2 | • Where a pointer address has been updated but no pointer/ renumbering case closed, because of an In progress Rating case - e-mail for info should be sent to the person the case is allocated to EO2 if possible • ideally comments field could be updated - or stages tab to alert valuer to change | ISG | Complete
RFC 2013-004 | 2013-03-11 | NIHE Housing Stock Asset Valuation Exercise 2012-13 | 1 | set up the Project/Sub-Projects/Cases structure on AO for the NIHE Housing Stock Exercise | ISG | Complete
NDR 2012 -007 | 2013-03-11 | Develop NDR FOR Test Plan | 1 | Develop NDR FOR Test Plan | ISG | Complete
NDR 2012-005 | 2012-12-31 | Migrate 2222 Data back to 2015 | 1 | 1) Migrate all relevant AO data that was moved to 01-04-2222 in the aborted raeval back to 01-04-2015 2) Establish the 7th List from that date 3) Identify all properties added to AO since aborted Reval, those demolished and those amended for data cleansing purposes | ISG | March 2013: Data moved to current list. New RFC needed for next stage.
NDR 2013-013 | 2013-04-01 | FOR Baseline Addresses | 1 | update Non-Dom addresses in AO with Gerry / Herbie's enhanced address set, which forms the baseline dataset for FOR addresses on the web. |  | Complete
RFC 2013-005 | 2013-03-01 | Certificate Amendments | 1 | Amendments to AO Certificates and Letters as a result of new headed paper |  | Complete
NDR 2013-012 | 2013-04-01 | N'hoods for Bulk Class Properties | 1 | Neighbourhoods for Bulk Class Properties |  | Complete
NDR 2013-014 | 2013-04-03 | Transaction Viewer Change | 1 | Lease Term no longer mandatory |  | Complete
RFC 2013-009 | 2013-05-03 | Update NIVT telephone number on Val. Certs | 1 | The telephone number for the NIVT has been updated to 028 90724857 The certificate types affected are: R12HQ R15HQ R21C – Dom & Mixed R21D – Dom & Mixed R24C – Dom & Mixed |  | complete
NDR 2012-002 | 2013-05-29 | Online FoR | 1 | Forms of Return on the web. | ISG/NDR | Complete
NDR 2012-011 | 2013-05-29 | NDR: Class/Sub Class/Type Validation | 1 | Data cleansing/validation for Class/Sub Class/ Type combinations once agreed by NDR and VMG | ISG/NDR | Complete
RFC 2013-006 | 2013-05-29 | Addition of ABBACUS Revision Request Reason to Case Viewer | 1 | Addition of ABBACUS Revision Request Reason to Case Viewer | ISG IMS | Complete
NDR 2012-008 | 2013-07-02 | AO- Web Recon for ND Properties | 1 | Ensure web valuations mirror AO/Abbacus valuations- Ratepayer should see on web the valuation used to calculate bills. Completed Monthly | ISG | Complete
RFC 2012-049 | 2013-07-02 | Fermanagh Addressing | 1 | Results of Fermanagh Addressing Project incorporated into Pointer by 31/03/13: mass update of AO will be required as a consequence. | IMS ISG POINTER | Complete
NDR 2013-009 | 2013-07-02 | NDR Data Cleansing - Mass Updates | 1 | NDR Data Cleansing - Mass Updates | NDR ISG | Complete
RFC 2013-007 | 2013-07-02 | Test Boundary Change Funct. between AO & ABBACUS | 2 | Test Boundary Change Functionality between AO and ABBACUS | ISG R&B | Complete
NDR 2013-018 | 2013-07-02 | Form of Return Reports | 1 | Monitoring of FOR completion | ISG | Complete
NDR 2012-12 | 2013-08-14 | FOR Data Mapping to AO/Viewer Amendments/Business Rules | 1 | Enable automatic data transfer and prevent possible transcription errors | ISG NDR | Complete
NDR 2013-016 | 2013-08-14 | FOR - Input of Paper Submissions | 1 | FOR - Input of Paper Submissions | ISG NDR | Complete
NDR 2013-008 | 2013-08-14 | AO NDR Manual | 1 | AO NDR Manual to be made available under the 'help' button | NDR ISG | Complete
NDR 2013-010 | 2013-08-14 | NDR Data Cleansing - New Validation Rules | 1 | NDR Data Cleansing - New Validation Rules | NDR ISG | Complete
NDR 2012-004 | 2013-08-14 | Make N'hood Mandatory for ND Bulk Classes | 1 | Make Neighbourhood Mandatory for ND Bulk Classes | ISG IMS | Complete
RFC 2013-001 | 2013-08-14 | Completion Notice Appeal Case Validation | 1 | to prevent change of sub-type from Completion Notice Domestic or Completion Notice Non-Domestic once a CN has been cloned – this allows the sub-type to be amended to Appeal to the Commissioner but the case remains as a non-CR-creating case as the sub-type is still CN | ISG IMS | Complete
RFC 2013-008 | 2013-08-14 | NIHE Exercise Case Closure | 1 | Routine mass closure of NIHE cases | ISG IMS | Complete
NDR 2013-019 | 2013-08-14 | FOR Data Files Preparation | 1 | FOR Printer Files, email datasets and Verification of additions to the process | ISG | Complete
NDR 2013-002 | 2013-10-11 | Migration of DA/CALc to AO Sever | 1 | August 2013: Needs to be completed before NDR 2013-006. Aim to is to have this completed by end of August. October 2013: Complete | ISG | October 2013: Complete
RFC 2013-021 | 2013-10-11 | 2013 Annual AO Disaster Recovery Test | 1 | 2013 Annual AO Disaster Recovery Test | ISG | October 2013: Complete
NDR 2013-026 | 2013-10-11 | Management Reports | 1 | Management Reports as per Trim Doc: DF1/13/537475 | ISG NDR | October 2013: Complete
RFC 2013-020 | 2013-10-11 | Combining CR changes from multiple RFC's | 1 | Combining CR changes from multiple RFC's to TFS to control and prepare the release of the CR changes when needed to coincide with the other system amendments required to populate the CR file. | ISG | October 2013: Complete
NDR2013-028 | 2013-10-11 | Data Cleansing SY Val Line data | 1 | Removal of data from Val Walls and Val Roof fields for SY Val Lines | NDR/ISG | October 2013: Complete
NDR 2012-013 | 2013-10-11 | NDR Skills Transfer Dev Express | 1 | NDP Skills Transfer | ISG IMS | October 2013: Complete
RFC 2013-014 | 2013-10-11 | Handling Merged/Derelict Properties in Pointer-AO interface | 3 | October 2013: OB to raise at new Pointer project- superceeded | IMS/ ISG/ POINTER | October 2013: Complete
see RFC 2013-013 | 2012-08-03 | PAO/SAO Restructuring | 3 | Superceeded as part of Logica workplan regarding Pointer & AO addresses. New RFC required November 2013 SUPERCEDED BY ADDRESS ALIGNMENT PROJECT | IMS/ ISG/ POINTER | Nov: 2012 - No Change October 2012: Process which is currently manual by Pointer to be automated. Work ongoing.
| 2013-09-11 | 2013-10-01 | Upload scanned FORs |  | 1 | 1 | Upload all scanned FORs into AO | ISG NDR | October 2013: To be done. SMG/MM to confirm priority. 11/11/2013 Now Deployed | Scanned record of actual completed FOR for audit and verification purposes | 2013-11-01
NDR 2013-029 | 2013-09-25 | 2013-10-31 | Close Down online FOR site |  | 1 | 1 | This FOR site is not behind the Departmental firewall and therefore must be either redesigned or shut down | NDR/ISG | October 2013: Provisional date for closing site is 1/11/13 Update 11/11/2013 Site now shut down. | To comply with Departmental website security protocol | 2013-11-01
RFC 2012-071 | 2012-09-19 | 2013-09-30 | Web update changes for appeals with subsequent cases |  | 2 | 3 | Web update changes for appeals with subsequent cases | ISG | October 2012: Addition Nov 2013, work completed | Ensure correct valuation is showing on Web at all times.
NDR2013-029 | 2013-10-08 |  | F.O.R Closing Date Notice |  |  |  | F.O.R Closing Date Notice |  | New October 2013 Update 11/11/13 Completed
RFC 2013-024 | 2013-10-17 |  | Provide linked PAO/SAO structure for Domestic Properties |  |  |  | Provide linked PAO/SAO structure for Domestic Properties |  | New October 2013. Update 11/11/13 Done
NDR 2013-003 | 2013-01-28 | 2013-11-18 | Reproduce FOR from AO using SSRS |  | 1 | 1 | Data for all FORs will be keyed in via the online form either by ratepayers or a dedicated LPS team inputting paper submissions so it will mean us creating a FOR template and then populating from the AO data | ISG NDR | October 2013: Initial testing complete. Back with ISG for more development. 11/11/13 Ready for deployment. | Will enable retrieval of data from online FORs to be reproduced in a printable format directly from AO | 2013-11-01 | 3.6 | Deployment
RFC 2012-068 | 2013-11-11 | 2013-11-18 | OD1 Form |  | 1 | 1 | LO1 forms generated by AO needs the 'Londonderry House' return address removed, and based on the council district the property is located - produce a form with the relevant return address. | ISG IMS | October 2013: AO Functionality complete, awaiting Abbacus release for 'go live'. Instructions currently being written. 11/11/13 Ready for deployment | Service Delivery Model outcome to collect ratepayer information at start of process will be achieved | 2013-11-01 | 3.6 | Deployment
RFC 2013-012 | 2013-11-11 | 2013-10-31 | Properties temporarily valued £0 in Valuation List |  | 1 | 1 | Properties temporarily valued £0 in Valuation List | IMS ISG | October 2013: Spec completed and in development. Aim to have in Test by w/c 14th October. 11/11/2013 Ready for deployment | Clarify AO procedure for dealing with these cases and ensure the procedure is suitable for Abbacus | 2013-11-01 | 3.6 | Deployment
NDR 2013-022 | 2013-11-11 | 2013-10-31 | Data Cleansing Cumulo Basis |  | 1 | 1 | In Property Part where Primary Class = 252 please mass update Type field from ‘Cumulo Basis’ to ‘Conventional’ | ISG NDR | October 2013: Development ongoing. JD working on this. 11/11/2013 Ready for deployment | Vital to be able to run analysis for office models in NDR | 2013-11-01 | 3.6 | Deployment
NDR 2013-025 | 2013-11-11 | 2013-11-30 | Transaction Viewer Amendments Phase II |  | 1 | 1 | Transaction Viewer Amendments Phase II | ISG NDR | October 2013: In Test Update 11/11/2013 Ready for deployment | Mirror changes in transaction viewer to Analysis Viewer | 2013-11-01 | 3.6 | Deployment
NDR 2013-024 | 2013-11-11 | 2013-12-31 | Transaction Viewer Validation Amendment |  | 1 | 1 | remove the mandatory validation on the landlord surname | ISG NDR | October 2013: in test. 11/11/2013 Ready for deployment pending go-ahead from NDR | Will remove workarounds currently needed by the user in the transaction viewer | 2013-11-01 | 3.6 | Deployment
RFC 2012-073 | 2013-11-11 | 2013-06-01 | Prevent Cloning of Data Cleansing Cases |  | 3 | 3 | Propid 600123 - a data cleansing case was cloned (which does not create a LE) into an Appeal to Commissioner case (6261856-1). Change to validation prevent the cloning of data cleansing cases - so users can't amend registration details | ISG IMS | October 2013: SMG to check if this has been completed. | Will prevent rejection by Abbacus of wrongly altered case types
NDR 2013-024 | 2013-08-06 | 2013-11-30 | 7th List Dual List Maintenance |  | 1 | 1 | 7th List Dual List Maintenance | ISG NDR | October 2013: Initial testing complete. Back with ISG for more development. | Enable dual list maintenance for NDR | 2013-12-01 | 3.7 | Deployment
NDR 2012-005 | 2013-09-11 | 31/11/2013 | NDR SPV generation flags set to False |  | 1 | 1 | AO SPV generation flags for aborted 2010 analysis need set to false again | ISG NDR | October 2013: In Test. | Prevent aborted rental analysis being used for NDR 2015 | 2013-12-01 | 3.7 | Deployment
NDR 2012-005 | 2013-09-04 | 2013-10-31 | Archiving NDR 2010 7th List |  | 1 | 1 | Archive 1/4/2222 List to set it beyond use | ISG/NDR | October 2013: In Test | Set the aborted reval list beyond use but still retrievable | 2013-12-01 | 3.7 | Deployment
RFC 2013-016 | 2013-06-17 | 2014-03-31 | Add date stamp to web application submissions |  | 1 | 1 | Amend the process of receipt of web applications to ensure that the date of submission of the application is recorded on each, and is used in the registration process | ISG | November 2013: Ongoing | Enable monitoring of statutory time limits for completion of personal applications | 2013-12-01 | 3.7 | Deployment
NDR 2013-020 | 2013-07-04 | 2013-12-31 | FOR Issue & Return Dates |  | 1 | 1 | issue and return date of FOR should be noted on the on the Property Viewer - Note tab (populate from Mailing Lists?) | ISG NDR | October 2013: Revised priority. Work to begin. | Audit of FOR activity to ensure traceability in the event of a challenge to the new list | 2013-12-01 | 3.7 | Deployment
NDR-2013-030 | 2013-11-01 | 2013-12-31 | Belfast shops 4 zones |  | 1 | 1 | Enable current shop zone C in Belfast to be split into C and D in respect of larger shops for NDR analysis and 7th List generation while retaining only 3 zones for 5th List | ISG/NDR | November 2013 |  | 2013-12-01 | 3.7 | Deployment
NDR 2013-021 | 2013-10-08 |  | CalC Stored Procedure rewrite (Data Refresh) |  | 1 | 1 | CalC Stored Procedure rewrite (Date Refresh) |  | 2013-10-01 |  | 2013-12-01 | 3.7 | Deployment
RFC 2013 - 025 | 2013-11-01 | 2013-12-31 | Belfast City Council Asset cases |  | 1 | 1 | Linking of individual Asset cases to project sub-projects similar to NIHE Asset exercise | ISG | November 2013 |  | 2014-01-01 | 3.8 | Deployment
| 2013-11-13 |  | Change wording on OD1 form |  | 1 | 1 | Wording on OD1 form in relation to occupiers of manses needs amending |  | November 2013 |  | 2014-01-01 | 3.8 | Deployment
NDR 2013-032 | 2013-12-05 |  | 821 Churches Data Extract |  | 1 | 1 | 821 Churches Data Extract | ISG | New: December 2013 |  | 2013-12-01 |  | Deployment
RFC 2012-072 | 2012-09-19 | 2013-12-31 | Amendment to CV rounding algorithm |  | 3 | 3 | District request as currently unable to enter any figure below £1000 in the domestic details Tab. Any figure below £1000 - should be the exact value | ISG | October 2013: In Test | Means the input of unusual values in AO won't need to be a manual insert by ISG
RFC 2013-034 | 2014-01-06 |  | Upload AO Align XML file into SQL for Verification |  |  |  | Work required to get the sample XML file and XSD schema into a useable state |  | New January 2014. 23/1/14 Now deployed. |  |  |  | Deployment

## Future Requirements (hidden)
|  | CAB WORKPLAN - Future Requirements |  |  |  |  | Last Updated: 03/05/2013
No. | Date | Requirement | Detail | Owner | BSC Target
1 |  | Scheme Tabs on AO | Review in line with new schemes. Schemes to be in place by 31/12/12 | IMS/ISG | N
2 |  | Dual List Maintenance for Penny Product |  | IMS/ISG | N
3 |  | Website Changes | Cater for Summary Valuations and 7th List Valuation List. File based valuations e.g. £20k X £1 not appropriate for summary valuations | IMS/ISG | N
4 |  | Data Management/Archiving | Good practice for improved system performance | ISG | N
RFC 2013-015 | 2013-06-17 | Re-skin Valuation List web Pages |  | ISG | N | 3 | 3 | Re-skin Valuation List web Pages | ISG | August 2013: Other work determined to be priority
NDR 2012-009 | 2012-12-17 | Summary Valuations | To be decided by NDR Project board | NDR/ISG | N | 3 | 3 | Summary Valuations | ISG IMS | Dec 2012: New Addition | Enable more detailed information available to the Ratepayer on the web
RFC 2013-014 | 2013-06-17 | Handling Merged / Derelict Properties in the Pointer to AO Interface | Whole issue of the AO functionality around merged/derelict property and how the AO/Pointer interface should work to complete the circle of an address life cycle | IMS/ISG | N |  |  | Handling Merged / Derelict Properties in the Pointer to AO Interface | IMS POINTER ISG | August 2013: Awaiting Spec

## Sheet1 (hidden)
Requirements
Design
Development
Testing
Documentation
Deployment

## Completed Jan -Feb 2014 (hidden)
CURRENT AO VERSION: 3.6 |  |  |  |  | Release Date: 28/02/2014 |  |  |  | Last Updated: 31/01/14 | 6 | 0 | 0 | 3
CAB WORKPLAN - Work In Progress
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014
RFC 2012-077 | 2012-12-19 | 2013-07-31 | Valuation Lists Site RMADS / ICT Health Check |  | 1 | 1 | Risk Management Accreditation Document Set. The PMQ1 form for the NDR Form of Return returned a Restricted status, so an RAMADS is now required for the site. DFP have contracted IT Guarded to undertake all future RMADS exercises. | ISG | May 2013: RMADS awaiting sign off with DR as information asset owner. Healthcheck for completed. IT Guarded want to test normal web submisssions to see if data can been accessed. October 2013: Signed off by DR subject to 1 amendment. PR to send to Dept Accreditor. 11/11/2013 Back with Philip Mulligan to amend key personnel on documents. 17/12/13 GO'B and PM reviewed the RMADS and sent back to Fiona Waterman. Not likely to be any further action needed. | Ensure security of FOR web access |  |  | Documentation | Complete | Complete
RFC 2013-028 | 2013-11-11 | 2013-12-31 | Select new domestic or new non domestic certificate following unticking of Temporary Incapable box following re-instatement of property |  | 1 | 1 | Temporary incapable properties reduced to zero are removed from Web List. On re-instatement of value the DV certificate selected should be that for new property. | ISG | New 11/11/2013. Update Dec 17th, small bug in testing but should be ready for December release. 23/1/14 ready to go | Ensure correct certificate selected | 2013-12-01 | 3.8 | Testing | Complete | Complete
RFC 2013-030 | 2013-11-13 |  | Web searching issues re: non domestic properties with no building number |  | 1 | 1 | Enable building name and building sub name to be displayed in web search results |  | 23/1/14 Tested and functioning for non domestic property. Ready for deployment by 28 Jan. New RFC to be raised for issues with domestic web searches. |  | 2014-01-01 | 3.8 | Testing | Testing - awaiting response | Complete
NDR 2013-006 | 2013-03-04 | 2013-10-31 | Calc System Amendments |  | 1 | 1 | Calc System Amendments | ISG IMS | October 2013: Revised Priority levels. Map Query work for NDR is considered priority. 23/1/14 now deployed | Amendments needed to mirror changes to valuation schemes | 2014-02-01 | 3.9 | Deployment | Ongoing - requirements | Complete
RFC 2013-031 | 2013-12-05 |  | Provide Performance Indicator data from AO for DataSpine Project |  | 1 | 1 | Provide Performance Indicator data from AO for DataSpine Project |  | 23/1/14 Deployed |  | 2014-02-01 | 3.7 | Deployment | Complete | Complete
RFC 2014-001 |  |  | NIHE Housing stock Exercise - case registration |  | 1 | 1 | Register 360 NIHE cases for mass Asset beacon inspection exercise | ISG | 23/1/14 Deployed |  | 2014-02-01 | 3.7 | Deployment | Complete | Complete
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...
NDR 2014-001 | 2013-01-30 |  | Pointer Email - 7th List Entry Address |  |  |  | Amend Pointer Email to update Future 7th list entry address on list creation |  | New January 2014 | [5 empty] | Complete
NDR 2014-002 | 2013-01-30 |  | DA Neighbourhood Report |  |  |  | Enable Neighbourhood Outturn Report DA2015 |  | New January 2014 |  |  |  |  | Complete - Connor | Complete
NDR 2014-004 | 2013-01-30 |  | Fire SSRS from within DA2015 |  |  |  | Fire SSRS from within DA2015 |  | New January 2014 |  |  |  |  | Complete -connor | Complete
NDR 2014-003 | 2013-01-30 |  | Update DA2015 Reports |  |  |  | Update DA2015 Reports |  | New January 2014 | [5 empty] | Complete
NDR 2013-033 | 2013-12-05 |  | To enable DA 2015 Reports |  | 1 | 1 | To enable DA 2015 Reports. 23/1/14 to be deleted and 4 separate RFC's to be added to workplan. | ISG | 2013-12-01 |  | 2014-02-01

## Completed March 2014 (hidden)
CURRENT AO VERSION: 3.10 | [8 empty] | Last Updated: 11/03/14 | 3 | 0 | 0 | 0
CAB WORKPLAN - Completed Work - March
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014
NDR 2013-034 | 2013-12-17 | 2013-02-28 | Update Calc for Guest House Bed & Breakfast scheme |  | 1 | 1 |  | NDR/ISG | 23/1/14 on track. |  | 2014-02-01 | 3.9 | Deployment | Testing | Testing | Testing | Completed
NDR 2013-036 | 2013-12-17 | 2013-02-28 | Update Calc for Wind Turbine scheme |  | 1 | 1 |  | NDR/ISG | 23/1/14 on track. |  | 2014-02-01 | 3.9 | Deployment | Went back for more requirements | With Gareth Neill | Development | Completed
| 2013-09-18 |  | Data Cleansing Masts |  | 1 | 1 | Further mass data cleansing non bulks eg masts to be considered after district cleansing plans submitted on 27/9/13 |  | September 2013. 20/2/2013 deployed |  | 2014-02-01 | 3.8 | Deployment |  |  | Development | Completed
NDR 2013-035 | 2013-12-17 | 2013-02-28 | Update Calc for Self Catering Accommodation scheme |  | 1 | 1 |  | NDR/ISG | 23/1/14 on track. |  | 2014-02-01 | 3.9 | Deployment | Testing | Testing | Testing | Testing
RFC 2014-008 | 2014-02-24 |  | Mass registration of exempt review cases as project/sub-project |  | 1 | 1 | OB to obtain details of properties to be registered from Exempt review team and provide to ISG | ISG IMS | 20/02/14 exempt review due to begin w/c/3/3/14 and 10/3/14.Case registration to be ready for w/c 3/3/14 |  | 2014-03-01 | 3.9 | Deployment |  |  |  | Awaiting response from Orla | Awaiting response from Orla | Testing | Updated and sent back to Testing | Complete
RFC 2013-033 | 2013-09-04 | 2014-03-31 | Pubs tabs on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team. 23/1/14 Spec received and work ongoing. On track |  | 2014-03-01 | 3.10 | Deployment | John - discussing with Gareth | Testing by wedensday | Still with testing | Still with testing | Development | Testing | Testing | Complete
NDR 2014-006 | 2013-09-04 | 2014-03-31 | Hotels tabs on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team 23/1/14 No spec yet received from reval team |  | 2014-03-01 | 3.10 | Deployment | Martin - ongoing | Testing | Still with testing | Still with testing | Still with testing |  | Testing | Complete
NDR 2014-016 | 2013-02-24 | 2013-02-28 | Update CALc for Sewage treament Works |  | 1 | 1 |  | NDR/ISG |  |  | 2014-02-01 | 3.8 | Deployment |  |  |  | Development | Testing | Testing | Complete
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...

## Completed April 2014 (hidden)
CURRENT AO VERSION: 3.10 | [8 empty] | Last Updated: 28/04/14 | 3 | 0 | 0 | 0
CAB WORKPLAN - Completed Work - April
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014
NDR 2014-010 | 2013-02-24 | 2013-02-28 | Update Calc for Residential Care Estblishments scheme |  | 1 | 1 |  | NDR/ISG | 20/2/2014 Will be ready for deployment end w/c/3/3/14 |  | 2014-02-01 | 3.8 | Deployment |  |  | Development | Awaiting Spec from Orla | Testing |  | Testing |  |  | Completed | Completed
RFC 2014-005 | 2014-01-30 | 2014-02-28 | MST Tender Verification Pack creation |  | 1 | 1 | MST Tender Verification Pack creation | ISG IMS | XSD files created and sample PIDS provided for ISG to create XML documents | MST Verification | 2014-02-01 | 3.09 | Deployment | Niall | Ongoing | Meeting with Orla 24 Feb | Testing | Testing | Testing | Testing |  |  | Testing | Testing
RFC 2014-002(???) | 2014-01-14 | 2014-03-31 | Address Alignment Verification Process |  | 1 | 1 | Address Alignment Verification Process | ISG | Filtering system build - development of Phase II, AO data massaging in progress | Address Alignment | 2014-03-01 | 3.10 | Deployment | Speak to Steven | meeting with sharon on Thursday | Speak to stevie | Speak to stevie | Ongoing | 16 out of 26 done in AO |  |  |  | S.T.S | S.T.S
RFC 2013-018 | 2013-08-06 | 2014-03-31 | RPA New Council Boundaries |  | 1 | 1 | RPA New Council Boundaries | ISG IMS | October 2013: Pointer project may supercede this point. OB to raise issues with interface for AO & Abbacus on newly created board Update 11/11/2013 ISG to look at fields needed for new councils and wards in AO. 23/1/14 OB to spec requirements for ISG | Enable new councils to be recorded against each property | 2014-03-01 | 3.9 | Deployment | Ongoing | Ongoing | Martin with help from Noel | Ongoing | Testing | Testing | Testing | Back with Development | Complete | Completed | Completed
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...
NDR 2014-019 | 2014-03-11 |  | Garden Centre Val Lines Import |  |  |  | Additional Val Lines that were created in CALc 2010 for 'Garden Centres, to be extracted and rentered in CALc 2015 |  | 18/4/14 Completed |  | 2014-04-01 |  | Deployment | [6 empty] | Conor looking at this | Conor looking at this |  | Conor & Stevie looking at this
RFC 2014-020 | 2014-04-15 |  | Final Class/SubClass/Type Combinations |  |  |  | Final List of Class/ Sub Class/ Type has been confirmed. The help button on AO should bring the user to this list. |  | New April 2014 Ongoing work |  | 2014-04-01 |  | Deployment

## Completed May 2014 (hidden)
CURRENT AO VERSION: 3.11 | [8 empty] | Last Updated: 07/05/14 | 3 | 0 | 0 | 0
CAB WORKPLAN - Completed Work - May
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014
NDR 2014-013 | 2013-02-24 | 2013-02-28 | Update Calc for Churches scheme |  | 1 | 1 |  | NDR/ISG | 20/2/2014 Will be ready for deployment end w/c/3/3/14 21/3/14 Specification of widget just received from NDR on 20 March. 18.4.14 ISG still awaiting final specification from NDR |  | 2014-02-01 | 3.8 | Deployment |  |  | Development | Awaiting Spec from Orla | Awaiting Spec from Orla | Received Spec from Sharon 20/03/2014 | Development | Development
NDR 2014-014 | 2013-02-24 | 2013-02-28 | Update Calc for Masts scheme |  | 1 | 1 |  | NDR/ISG | 20/2/2014 Will be ready for deployment end w/c/3/3/14 |  | 2014-02-01 | 3.8 | Deployment |  |  | Development | Awaiting Spec | Awaiting Spec | Updated Spec after Stevie spoke to Norman 20/03/2014 | Norman meeting with conor | Conor working on this | Testing | Complete, although conor thinks it may need more testing | Deployed
NDR 2014-008(???) | 2014-01-28 |  | Update lookup fields to ensure all valid options mirror that in ao |  | 1 | 1 |  | NDR/ISG |  |  | 2014-02-01 | 3.8 | Deployment |  |  |  | Ongoing | Development |  | Development | Development | Conor looking into this | Ongoing | Johns looking at this
NDR 2014-018 | 2014-02-28 |  | Update Calc for AD stations scheme |  | 1 | 1 |  | NDR/ISG |  |  | 2014-02-01 | 3.8 | Deployment |  |  |  | Development | Testing | Testing | Testing | Spec has been changed | Testing
RFC 2014-021 | 2014-05-12 |  | Auto Case closure for BCC asset cases |  | 1 | 1 |  | ISG |  |  | 2014-05-01 | 3.8 | Deployment
RFC 2013-010 | 2013-05-02 | 2014-01-31 | AO - ABBACUS Recon to include Classification Information |  | 1 | 1 | AO - ABBACUS Recon to include Classification Information | ISG IMS CAB | October 2013: Revised Priority levels. Awaiting NDR data cleansing exercise to be completed. Update 17/12/13 AMCG sent download of data to JF this week. JF will perform recon to identify SBRR issues. 2 weekly recon files will be produced from this point onwards, normal one going to live. Second one with c/s/t for testing. 23/1/14 JF due to recon with monthly AO/Abbacus recon file by W/E 31 Jan and advise results to CAB. 20/2/14 R&B recon delayed, now due to take place w/c 24/2/14. ISG to provide an up to date extract to enable this. 21/3/14 data extract provided to R&B on 28 Feb. No feedback to date. 26/3/14 JF to check where file to ICS went to. Seems to be no trace of it. To advise outcome and if necessary to request new file.18.4.14 Recon results have been sent to ISG, around 15k mismatches. To be followed up at CAB. | Improve the quality of the reconciliation between AO and Abbacus | 2014-02-01 | 3.8 | Deployment | Waiting response from Jo Fullerton | Ongoing | Speak to stevie | Ongoing | Awaiting response from Revenues & Benefits |  |  | S.T.S | S.T.S | S.T.S |  | S.T.S
NDR 2014-015 | 2013-02-24 | 2013-02-28 | Update Calc for Halls scheme |  | 1 | 1 |  | NDR/ISG | 20/2/2014 Will be ready for deployment end w/c/3/3/14 21/3/14 Waiting on details of cost guide from NDR. 26/3/14 Scheme author has sent it to his line manager but she needs to confirm a few things on it first. A quality check is needed. 18/4/14 In test with scheme author |  | 2014-02-01 | 3.8 | Testing |  |  | Development | Development | Awaiting Figures |  | Requirements | Requirements | Awaiting requirements | Still awaiting requirements | Received spec on Friday 9th May | Conor working on this
RFC 2014-013 | 2013-10-12 |  | Put checks in place in web applications alerting RTL of cases closed in previous 35 days |  | 1 | 1 | Ensure web applications which may be Appeals to COV are trapped and registered as Appeals. |  | October 2013. 23/1/14 No further progress 26/3/14 Pushed back to June due to other ongoing work 18/4/14 No progress |  | 2014-06-01 | 3.12 | Requirements | [13 empty] | Speak to Stevie
RFC 2014-019 | 2014-04-15 |  | Lanyon Plaza server move |  | 1 | 1 | Lanyon Plaza server move |  | New April 2014 | [12 empty] | Noel/John/Martin | Ongoing | Noel drawing up spec | Completed for AO awaiting input from Herbie | Ongoing
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...

## Completed June 2014 (hidden)
CURRENT AO VERSION: 3.11 | [8 empty] | Last Updated: 07/05/14 | 3 | 0 | 0 | 0
CAB WORKPLAN - Completed Work - June
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014
RFC 2014-022 |  |  | Analysis ID |  |  |  |  | ISG | New June 2014 |  |  |  | Deployment
RFC 2013-033 (NDR 2013-031) | 2013-09-04 | 2014-03-31 | Pubs tabs on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team. 23/1/14 Spec received and work ongoing. On track. 20/2/14 In test 21/3/14 In development. 26/3/14 Functionality is OK, any amendments needed will be to percentages in the matrix, and this is arising from analysis of accounts not yet received by scheme author. Once these are known it will be a small change request to amend the percentages. Functionality can be deployed. 18/4/14 No change still awaiting updates from scheme author.30/5/14 In development, Spec received by ISG on 27/5/14.Some functionality changes required. To be in test by Wed 4th June |  | 2014-03-01 | 3..9 | Deployment | [7 empty] | ?????? | Testing with Gareth | Need to speak to John | John - Should be finished by the end of the week. | John - Still working on this - going to be discussed at Skills transfer.
RFC 2013-032 | 2013-09-04 | 2014-03-31 | PFS tab on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team.23/1/14 Spec received and work ongoing. On track 20/2/14 In test. 21/3/14 Waiting feedback from NDR/Scheme Author. 18/4/14 No change, but looks as though there will be the need to amend functionality following on from Reval technical group meeting, second threshold to be inserted for petrol throughput. 30/5/14 Testing and bug fixing ongoing. |  | 2014-05-01 | 3.10 | Deployment | Noel - half way through | Testing | Still with testing | Still with testing | Testing | Testing | Back with Development | Martin sent email to Gareth for feedback
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...

## Completed July 2014 (hidden)
CURRENT AO VERSION: 3.11 | [8 empty] | Last Updated: 07/05/14 | 0 | 0 | 0 | 0
CAB WORKPLAN - Completed Work - July
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014
NDR 2014-005(???) | 2013-01-30 |  | DA2015 Audit Reports |  | 1 | 1 | Create DA2015 Audit Reports |  | New January 2014 |  | 2014-03-01 | 3.11 | Deployed |  | John | Ongoing | Development | Development | J and C looking into this | John 70% done | John and Conor meeting on Thursday 1 | John working on this - will be finished by 1st June | Ongoing | John Waiting on Conor for Guidance | Ongoing | John is debuging - will need to speak to Conor | Functionality is complete Automation Could take up to 2 weeks | Conor working on interface - should be completed by Friday | John will finish today
NDR 2014-017 | 2013-01-30 |  | GR Files from AO to Abbacus |  | 1 | 1 | Generation of the general revaluation (GR) file from AO to abbacus |  | New January 2014 21/3/14 Meeting in ISG to discuss this today 26/3/14 On track. JF requested that R&B would get ongoing files to track changes. 18/4/14 On track will be ready by April deployment date. 30/5/14 first file produced, some duplicates and potential bugs. ISG working through these and will decide who and what action needed when further information is known |  | 2014-05-01 | 3.11 | Deployment
RFC 2014-033 | 2014-07-08 |  | Archive of 311 Class properties in CALc |  |  |  | Archive of 311 Class properties in CALc |  | NEW* Source archived S&R information from CALc 2010 |  |  | 3.11 | Deployment | [16 empty] | John- Should be finished 1-2 days
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...

## Completed August 2014 (hidden)
CURRENT AO VERSION: 3.11 |  |  |  |  | Release Date: 02/08/2014 |  |  |  | Last Updated: 12/08/14 | 18 | 5 | 4 | 4
CAB WORKPLAN - Work In Progress
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC | Date Added | Expected Completion Date | Issue | BSC Target | BusinessPriority | Action Priority | Details | Action | Update | Identified Benefit | Planned AO Release Date | AO Release Version | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014 | Update 10-03-2014 | Update 20-03-2014 | Update 24-03-2014 | Update 31-03-2014 | Update 04-04-2014 | Update 14-04-2014 | Update 28-04-2014 | Update 06-05-2014 | Update 12-05-2015 | Update 20-05-2014 | Update 27-05-2014 | Update 29-05-2014 | Update 03-06-2014 | Update 09-06-2015 | Update 16-06-2015 | Update 01-07-2015 | Update 08-07-2016 | Update 21-07-2017 | Update 28-07-2018 | Update 05-08-2019 | Update 05-08-2020
NDR 2014-013 | 2013-02-24 | 2013-02-28 | Update Calc for Churches scheme |  | 1 | 1 |  | NDR/ISG | 20/2/2014 Will be ready for deployment end w/c/3/3/14 21/3/14 Specification of widget just received from NDR on 20 March. 18.4.14 ISG still awaiting final specification from NDR 30/5/14 Possibly no need for widget in Calc as will be done directly in AO. NDR team to confirm by 6/6/14 23/7/14 This RFC is being closed. CALc Widget not required. New RFC created for mass updating of data for churches from spreadsheets into AO |  | 2014-02-01 | 3.8 | Deployment | [21 empty] | Complete | Complete | Complete | Complete
RFC 2013-032 | 2013-09-04 | 2014-03-31 | PFS tab on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team.23/1/14 Spec received and work ongoing. On track 20/2/14 In test. 21/3/14 Waiting feedback from NDR/Scheme Author. 18/4/14 No change, but looks as though there will be the need to amend functionality following on from Reval technical group meeting, second threshold to be inserted for petrol throughput. 30/5/14 Testing and bug fixing ongoing. 23/7/14 Deployed, but some bugs advised to ISG. |  | 2014-05-01 | 3.9 | Deployment | [21 empty] | Complete | Complete | Complete | Complete
NDR 2013-031 | 2013-09-04 | 2014-03-31 | Pubs tabs on AO need amending |  | 1 | 1 | Amendments needed to reflect NDR 2015 schemes | ISG NDR | September 2013: New Addition to be spec'ed by Reval team. 23/1/14 Spec received and work ongoing. On track. 20/2/14 In test 21/3/14 In development. 26/3/14 Functionality is OK, any amendments needed will be to percentages in the matrix, and this is arising from analysis of accounts not yet received by scheme author. Once these are known it will be a small change request to amend the percentages. Functionality can be deployed. 18/4/14 No change still awaiting updates from scheme author.30/5/14 In development, Spec received by ISG on 27/5/14.Some functionality changes required. To be in test by Wed 4th June 23/7/14 Deployed. |  | 2014-03-01 | 3.9 | Deployment | [21 empty] | Complete | Complete | Complete | Complete
NDR 2014-017 - Regenerating GR file | 2013-01-30 |  | GR file from AO to Abbacus |  |  |  | Generation of the General Revaluation (GR) File from AO to Abbacus |  | New January 2014 21/3/14 Meeting in ISG to discuss this today 26/3/14 On track. JF requested that R&B would get ongoing files to track changes. 18/4/14 On track will be ready by April deployment date. 30/5/14 first file produced, some duplicates and potential bugs. ISG working through these and will decide who and what action needed when further information is known 23/7/14 Deployed |  | 2014-05-01 | 3.10 | Deployment | [21 empty] | Complete | Complete | Complete | Complete
RFC 2013-027 | 2013-11-01 |  | Avgen/AO interface |  | 1 | 1 | Interface between Avgen and AO |  | November 2013 23/1/14 On Track. 20/2/2014 Valuation of schools etc on Avgen to be completed by end of March 14. However transfer of data back to AO not needed then. Re-scheduled for May release. 30/5/14 In development - download of data received from AVGEN. |  | 2014-06-01 | 3.10 | Requirements |  |  |  | Speak to Steven | Awaiting response from Barry O'Donnell | Awaiting response from Barry O'Donnell | Awaiting response from Barry O'Donnell |  |  | No change | S.T.S |  | S.T.S |  | S.T.S |  | Stevie developing | Stevie developing | Stevie developing | Stevie developing |  | Awaiting Deployment Notes | Awaiting Deployment Notes | Awaiting Deployment Notes | Complete
NDR 2013-007 | 2013-03-04 | 2014-04-01 | Calc Interface with AO |  | 1 | 1 | Calc Interface with AO | NDR ISG | March 2013: Addition 23/1/14 On track 20/2/2014 Valuation of Non bulks etc on Avgen to be completed by end of March 14. However transfer of data back to AO not needed then. Re-scheduled for May release. 30/5/14 Spec'ed and now in development | Amendments needed to mirror changes to valuation schemes | 2014-06-01 | 3.10 | Requirements | Speak to Steven |  | Development | pre Requirements stage | Ongoing |  | Design |  |  | Gathering Requirements | Requirements | Conor &Martin looking at this | Conor &Martin looking at this | Martin working on extracting the files from CALc | Ongoing | Ongoing | with Conor for Development | Early stages of Development | Extracts done. Passed to Noel for further development | Stevie developing |  | Development | Development | Development | Complete
RFC 2014-028 | 2014-05-29 |  | Problem with CV clearing out of Summary tab during in progress cases for mixed properties |  | 1 | 1 | New May 2014 Log file sent to ISG to investigate |  |  |  | 2014-06-01 | [24 empty] | John needs to look at this | Complete | Complete
RFC 2014-026 | 2014-05-29 |  | Amendments of LPS addresses on certificates generated out of AO for move to Lanyon Plaza |  | 1 | 1 | New May 2014 OB specifying changes required. |  | 23/7/14 In test |  | 2014-06-01 |  | Testing | [23 empty] | Complete | Complete
RFC 2014-013 | 2013-10-12 |  | Put checks in place in web applications alerting RTL of cases closed in previous 35 days |  | 1 | 1 | Ensure web applications which may be Appeals to COV are trapped and registered as Appeals. |  | October 2013. 23/1/14 No further progress 26/3/14 Pushed back to June due to other ongoing work 18/4/14 No progress 23/7/14 Deployed |  | 2014-06-01 | 3.12 | Deployment | [21 empty] | Complete | Complete | Complete | Complete
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
RFC 2014-038 | 2014-04-18 |  | Add new Wards tables to AO for 2015 RPA to AO prior to reval publication in November |  |  |  | Need these to be added to AO to ensure that search facility for Web valuation List for 2015 can be done on new council structure. Will need to retain both old and new structures in AO tables. | IMS/ ISG | New April 2014 |  | 2014-09-01 |  | Deployment | [24 empty] | Complete
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...
RFC 2014-029 | 2014-07-08 |  | 6th and 7th List comparision |  |  |  | Compile a list of all 6th list non domestic entries which do not have a 7th list non domestic entry |  | NEW* Compile a list of all 6th list non domestic entries which do not have a 7th list non domestic entry | [25 empty] | Noel Meeting with Mary 21st july - on hold until Sharon returns | Noel Meeting with Mary 21st july - on hold until Sharon returns | Awaiting feedback from Sharon | Complete
RFC 2014-031 | 2014-07-08 |  | Cosmetic Changes to the Pubs Tab in AO |  |  |  | Cosmetic Changes to the Pubs Tab in AO |  | NEW* Cosmetic Changes to the Pubs Tab in AO | [25 empty] | Ready for deployment | Deployed | Complete | Complete
RFC 2014-033 | 2014-07-08 |  | Archive of 311 Class properties in CALc |  |  |  | NEW* Archive of 311 Class properties in CALc |  | NEW* Source archived S&R information from CALc 2010 | [25 empty] | Deployed | Deployed | Complete | Complete
RFC 2014-035 | 2014-07-08 |  | Amend Decaps rates in CALc |  |  |  | Amend Decaps rates in CALc |  | NEW* Apply new Decap rate to widget | [25 empty] | Conor started work on this |  | Complete | Complete
RFC 2014-036 | 2014-07-08 |  | Decaps for ECVs for SHORT Matrix |  |  |  | Decaps for ECVs for SHORT Matrix |  | NEW* Apply new Decap rate to widget | [25 empty] | Conor started work on this |  | 75% Complete | Complete
RFC 2014-032 | 2014-07-08 |  | AO NDR platform to collate 7th List valuations from all NDR systems |  |  |  | Satellite Systems (Daily Running Totals AO/Avgen/CALc) |  | NEW* Create a snapshot of AO/Avgen/CALc to give daily running totals pending the official upload of all data into AO | [25 empty] | Martin - Requirements |  | Design | Complete
RFC 2014-040 | 2014-08-11 |  | Data Extracts for non-domestic hereditaments including list entry addresses |  |  |  | NEW* Two data extracts of non-domestic hereditaments (hereditament flag = true)and their List Entry addresses as at (1) 1/2/2014 and (2) 15/7/2014 Required to identify before and after changes to non-domestic addresses in respect of impact on ratepayer marketing for NDR 2015. | [30 empty] | Complete
Not on CAB
RFC 2014-034 | 2014-07-08 |  | Repository for PFS attachments |  |  |  | Repository for PFS attachments |  | NEW* Set up Repository for PFS attachments and upload into AO | [25 empty] | Martin - Requirements |  | Complete | Complete
RFC 2014-038 | 2014-07-23 |  | New Councils/Wards lookup tables |  |  |  | NEW* New Councils/Wards lookup tables to be built into AO for creating new addresses in address viewer from 1/4/15 | [29 empty] | Noel- Development | Noel- Development

## Completed September 2014 (hidden)
CURRENT AO VERSION: 3.11 |  |  |  |  | Release Date: 02/08/2014 |  |  |  | 9 |  | 2 | 8 | 11
CAB WORKPLAN - Work In Progress | [8 empty] | Last Updated: 12/08/14
RFC | Date Added | Expected Completion Date | Title | BSC Target | BusinessPriority | Priority | Request Overview | Action | Update | Identified Benefit | Release Month | AO Build | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014 | Update 10-03-2014 | Update 20-03-2014 | Update 24-03-2014 | Update 31-03-2014 | Update 04-04-2014 | Update 14-04-2014 | Update 28-04-2014 | Update 06-05-2014 | Update 12-05-2015 | Update 20-05-2014 | Update 27-05-2014 | Update 29-05-2014 | Update 03-06-2014 | Update 09-06-2015 | Update 16-06-2015 | Update 01-07-2015 | Update 08-07-2016 | Update 21-07-2017 | Update 28-07-2018 | Update 05-08-2019 | Update 05-08-2020 | Update 15-09-2021
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC 2013-022 | 2013-10-01 | 2013-12-31 | Amend Pointer Email to include Before and New List entry Address |  | 1 | 1.1 | Issue Pointer Email to include Before and New List entry Address | ISG | Ready for deployment pending release nots from MM | Ensure RTL can take quick action if Pointer address changes are a cause of concern | 2014-11-01 | 3.11 | Testing | Need to speak to Stevie |  | Requirments | Speak to steven | Ongoing | Testing | Testing | Back with Development |  | Development | Ongoing | Ongoing | Ongoing |  | Ongoing | Stevie is developing this | Under Development | Under Development | Under Development | With Mary for specification | With Mary for specification | Awaiting Deployment Notes | Awaiting Deployment Notes | Awaiting Deployment Notes | Awaiting Deployment Notes | Deployment
RFC 2014-045 | 2014-09-09 |  | 2014 Annual AO Contingency & Data Recovery Testing |  |  |  | NEW* Annual AO Contingency Testing | ISG |  |  |  | 3.11 | Development | [25 empty] | Martin working on documentation
RFC 2014-004 | 2013-10-12 |  | Acknowledgement letter for review of Exempt properties |  | 1 | 1.1 | Draft letter provided by Peter Clifford in respect of review of exempt properties | ISG & IMS | With OB for final testing |  | 2014-11-01 | 3.11 | Testing | John | Stevie | Development | Testing | Development | Testing | Spec keeps changing - need to discuss further. |  |  | Conor in Discussions with Angela | Ongoing | Received Spec Me & Noel will look at this | Conor working on Spec - needs input from sharon | John Working on this - needs to be completed by 30th May at the latest | Ongoing | John only received spec this week | Under Development | Stevie and John working on this | Skills trnasfer session 17th June to redevelop | Will be finished by Friday at the latest | With Orla for testing (7th July) | John to speak to Orla today back with development | John spoke to Orla 23 July - nothing since. Still with testing |  | Martin phoned and email Orla today to gauge progress | Sent to Orla for testing
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
RFC 2011-128 | 2013-07-31 | 2013-07-31 | Pro-forma correspondence generated by AO |  | 2 | 3.3 | • Extension notices for A3 cases • Letter requesting further information from appellants when appeal form has not been fully completed | IMS & ISG | Specification Completed. No further progress due to higher priority work | Automating a manual process for appeals in line with CR cases | 2015-04-01 |  | Development |  | Needs Spec | To be looked at | To be looked at
RFC 2013-011 | 2013-05-08 | 2014-03-31 | Mandatory Occupation Status on Case Closure |  | 3 | 3.3 | compulsory prior to closing a case to record whether a property is owner occupied, tenanted, unknown and where tenanted is selected, a transaction is recorded | IMS & ISG | Business spec provided awaiting technical spec. Other work determined to be a priority | Enforce collection of rental information on AO | 2015-04-01 |  | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements | Requirements
NEW ADDITIONS WAITING TO BE SPECIFIED...
NDR 2014-029 | 2014-08-11 |  | NDR email correspondence |  |  |  | NEW* NDR email correspondence | ISG | NEW | [29 empty] | Stevie
NDR 2014-033 |  |  | Allow Manual update of RATE for RCE Calc Properties (short-term |  |  |  | Allow Manual update of RATE for RCE Calc Properties (short-term | ISG | NEW
Not on CAB

## Completed October 2014 (hidden)
CURRENT AO VERSION: 3.11 |  |  |  |  | Release Date: 02/08/2014 |  |  |  | 1 |  | 0 | 0 | 0
CAB WORKPLAN - Work In Progress | [8 empty] | Last Updated: 14/10/14
RFC | Date Added | Expected Completion Date | Title | BSC Target | BusinessPriority | Priority | Request Overview | Action | Update | Identified Benefit | Release Month | AO Build | Status | Update 10-02-2014 | Update 17-02-2014 | Update 24-02-2014 | Update 03-03-2014 | Update 10-03-2014 | Update 20-03-2014 | Update 24-03-2014 | Update 31-03-2014 | Update 04-04-2014 | Update 14-04-2014 | Update 28-04-2014 | Update 06-05-2014 | Update 12-05-2015 | Update 20-05-2014 | Update 27-05-2014 | Update 29-05-2014 | Update 03-06-2014 | Update 09-06-2015 | Update 16-06-2015 | Update 01-07-2015 | Update 08-07-2016 | Update 21-07-2017 | Update 28-07-2018 | Update 05-08-2019 | Update 05-08-2020 | Update 15-09-2021
PRIORITY 1 CURRENT SUBSTANTIAL ACTION
RFC 2014-043 | 2014-08-19 |  | Produce Aligned/Unaligned valuation list files for POINTER |  |  | 1.1 | NEW* Produce Aligned/Unaligned valuation list files for POINTER | ISG | NEW |  | 2014-11-01 | 3.11 | [26 empty] | Noel
RFC 2014-044 | 2014-08-19 |  | Produce Valuation list file with new RPA District/ Ward fields for ABBACUS |  |  | 1.1 | Produce Valuation list file with new RPA District/ Ward fields for ABBACUS | ISG | NEW |  | 2014-11-01 | 3.11 | Deployment | [25 empty] | Noel
NDR 2014-030 | 2014-08-19 |  | LRFV Data extract for NDR web publication 7th List |  |  | 1.1 | NEW* Data extract for NDR web publication 7th List | ISG | NEW |  | 2014-11-01 | 3.11 | Deployment | [25 empty] | Martin & Conor
NDR 2014-032 | 2014-08-19 |  | DA Bulk Class Extract for Statisticians |  |  | 1.1 | Provide a Bulk Class Extract for Statisticians from DA | ISG | NEW |  | 2014-10-01 | 3.11 | Deployment | [25 empty] | Conor & Martin
NDR 2014-036 | 2014-08-19 |  | New fields added to the existing Reval Progress report in DA |  |  | 1.1 | New fields added to the existing Reval Progress report in DA | ISG | To assist with DV Review |  |  |  | Deployment
PRIORITY 2 SUBSTANTIAL ACTION 3-6 MONTHS
PRIORITY 3 SUBSTANTIAL ACTION 6+ MONTHS
NEW ADDITIONS WAITING TO BE SPECIFIED...
Not on CAB

## Queens 5
NORTH DOWN 2016/17 GRAND PRIX
Goddesses
2017-05-01 | Festival of Miles - 1 Mile
NAME | Event Points | Position Points | PB Points | Event Total | OVERALL TOTAL | Movement
McDonough, Valerie | 10 | 9 | 0 | 19 | 146 | ↔
Moran, Joanne | 10 | 10 | 5 | 25 | 139 | ↔
Stevenson, Jane | 10 | 7 | 5 | 22 | 98 | ↑
Smith, Clare | 10 | 3 | 5 | 18 | 96 | ↔
Simpson, Paula | 10 | 4 | 5 | 19 | 92 | ↑
McMeechan, Lisa |  |  |  | 0 | 88 | ↓
Byers, Helen |  |  |  | 0 | 75 | ↓
Wise, Alison | 10 | 5 | 5 | 20 | 68 | ↑
Smith, Jodi |  |  |  | 0 | 65 | ↓
Green, Andrea | 10 | 2 | 5 | 17 | 60 | ↑
Crothers, Caroline |  |  |  | 0 | 48 | ↓
Downey, Nicola | 10 | 8 | 5 | 23 | 45 | ↑
Cummings, Joanne | 10 | 6 | 5 | 21 | 41 | ↑
Benton, Sarah |  |  |  | 0 | 36 | ↓
Kerr, Lynne |  |  |  | 0 | 33 | ↓
McCausland, Noreen |  |  |  | 0 | 25 | ↓
Russell, Clare |  |  |  | 0 | 21 | ↓
Rodgers, Heidi |  |  |  | 0 | 19 | ↔
McDonnell, Elaine |  |  |  | 0 | 18 | ↔
Hodgson, Tracey |  |  |  | 0 | 16 | ↔
Blayney, Valerie |  |  |  | 0 | 15 | ↔
Blomley, Kathryn |  |  |  | 0 | 15 | ↔
Caughers, Gemma |  |  |  | 0 | 13 | ↔
Patton, Melanie |  |  |  | 0 | 12 | ↔
Devine, Marie |  |  |  | 0 | 11 | ↔
Sexton, Helen |  |  |  | 0 | 10 | ↔
Watson, Louise |  |  |  | 0 | 0 | ↔
Gods
2017-05-01 | Festival of Miles - 1 Mile
NAME | Event Points | Position Points | PB Points | Event Total | OVERALL TOTAL | Movement
Massey, David | 10 | 8 | 5 | 23 | 136 | ↔
McMeechan, Jamie |  |  |  | 0 | 110 | ↔
Caughers, Ben | 10 | 10 | 5 | 25 | 105 | ↑
Scott, Dennis |  |  |  | 0 | 97 | ↓
Mulligan, Philip |  |  |  | 0 | 87 | ↓
Walker, Colin |  |  |  | 0 | 78 | ↔
Massey, Alan |  |  |  | 0 | 73 | ↔
Wise, Steve | 10 | 6 | 5 | 21 | 72 | ↑
McMeechan, David |  |  |  | 0 | 71 | ↓
Gilmore, Keith |  |  |  | 0 | 67 | ↓
Rea, Frank |  |  |  | 0 | 64 | ↓
Stevenson, Michael |  |  |  | 0 | 60 | ↓
Ewing, John | 10 | 9 | 5 | 24 | 59 | ↑
McCausland, Cliff | 10 | 5 | 5 | 20 | 55 | ↑
O'Reilly, Eamonn |  |  |  | 0 | 51 | ↓
McMeechan, Craig |  |  |  | 0 | 50 | ↓
Weir, Mark |  |  |  | 0 | 50 | ↓
Hamilton, Darren |  |  |  | 0 | 47 | ↓
Frazer, Glenn |  |  |  | 0 | 45 | ↓
Geddis, Brian |  |  |  | 0 | 39 | ↓
Brown, Mitchell |  |  |  | 0 | 30 | ↓
McGarvey, John |  |  |  | 0 | 30 | ↓
Donegan, Steven |  |  |  | 0 | 30 | ↓
Muir, Andrew |  |  |  | 0 | 27 | ↓
Moran, Chris | 10 | 7 | 5 | 22 | 22 | ↑
Galloway, Paul |  |  |  | 0 | 20 | ↓
Budde, James |  |  |  | 0 | 19 | ↓
Sexton, Simon |  |  |  | 0 | 16 | ↓
Martin, Rab |  |  |  | 0 | 10 | ↓
McClements, David |  |  |  | 0 | 10 | ↓
Ferguson, John |  |  |  | 0 | 0 | ↓
Matchett, Gordon |  |  |  | 0 | 0 | ↓
McDonnell, Gavin |  |  |  | 0 | 0 | ↓
Nelson, Scott |  |  |  | 0 | 0 | ↓
Patterson, Trevor |  |  |  | 0 | 0 | ↓